## Sheet1
activity_id | wbs | discipline | description | planned_start | planned_finish | location | status
PIP-001 | 1.1.1 | piping | 8 inch carbon steel pipe spool fabrication | 2026-07-01 | 2026-08-15 | Fab Yard Area A | in_progress
PIP-002 | 1.1.2 | piping | 6 inch stainless steel pipe installation - Unit 100 | 2026-07-15 | 2026-09-01 | Unit 100 - Rack R1 | not_started
PIP-003 | 1.1.3 | piping | Hydrostatic pressure testing of piping circuit PC-101 | 2026-09-05 | 2026-09-20 | Unit 100 | not_started
PIP-004 | 1.1.4 | piping | Weld joint completion for header H-201 | 2026-07-10 | 2026-08-30 | Unit 200 - Header Area | in_progress
PIP-005 | 1.1.5 | piping | Pipe support installation at pipe rack PR-01 | 2026-08-01 | 2026-09-15 | Pipe Rack PR-01 | not_started
PIP-006 | 1.1.6 | piping | Flange bolt-up and gasket installation line L-301 | 2026-09-01 | 2026-10-01 | Unit 300 | not_started
PIP-007 | 1.1.7 | piping | Insulation work on hot piping circuits | 2026-09-15 | 2026-10-30 | Units 100-300 | not_started
PIP-008 | 1.1.8 | piping | 4 inch utility piping installation - firewater | 2026-07-20 | 2026-09-10 | Utility Area | in_progress
PIP-009 | 1.1.9 | piping | Valve installation and tagging for Unit 200 | 2026-08-15 | 2026-09-30 | Unit 200 | not_started
PIP-010 | 1.2.1 | piping | Pigging and flushing of process lines | 2026-10-01 | 2026-10-20 | All Units | not_started
CIV-001 | 2.1.1 | civil | Reinforced concrete foundation for compressor C-101 | 2026-06-15 | 2026-08-01 | Compressor Area | in_progress
CIV-002 | 2.1.2 | civil | Earthwork and excavation for Unit 200 foundations | 2026-06-20 | 2026-07-30 | Unit 200 Plot | in_progress
CIV-003 | 2.1.3 | civil | Piling work for heavy equipment foundation | 2026-07-01 | 2026-08-15 | Equipment Area EA-1 | not_started
CIV-004 | 2.1.4 | civil | Underground cable trench construction | 2026-07-15 | 2026-09-01 | Main Cable Route | not_started
CIV-005 | 2.1.5 | civil | Control room building structural steelwork | 2026-08-01 | 2026-10-15 | Control Room Area | not_started
CIV-006 | 2.1.6 | civil | Pipe rack foundation and pedestal construction | 2026-06-25 | 2026-08-20 | Pipe Rack PR-01 | in_progress
CIV-007 | 2.1.7 | civil | Road and access way construction | 2026-07-10 | 2026-09-15 | Plant Access Roads | not_started
CIV-008 | 2.1.8 | civil | Fireproofing application on steel structures | 2026-09-01 | 2026-10-30 | All Units | not_started
CIV-009 | 2.1.9 | civil | Boundary wall and fencing installation | 2026-08-15 | 2026-10-01 | Plant Boundary | not_started
CIV-010 | 2.2.1 | civil | Storm water drainage system construction | 2026-07-20 | 2026-09-30 | Plant Wide | not_started
ELE-001 | 3.1.1 | electrical | Main power transformer installation 33kV/6.6kV | 2026-08-01 | 2026-09-30 | Substation Area | not_started
ELE-002 | 3.1.2 | electrical | HT cable pulling and termination 6.6kV | 2026-08-15 | 2026-10-15 | Cable Gallery CG-01 | not_started
ELE-003 | 3.1.3 | electrical | LT power cable laying for Unit 100 motors | 2026-07-15 | 2026-09-01 | Unit 100 MCC Room | not_started
ELE-004 | 3.1.4 | electrical | Motor control center MCC-01 installation | 2026-08-01 | 2026-09-15 | MCC Room 1 | not_started
ELE-005 | 3.1.5 | electrical | Lighting installation for process area | 2026-09-01 | 2026-10-30 | Process Areas | not_started
ELE-006 | 3.1.6 | electrical | Earthing and grounding grid installation | 2026-07-01 | 2026-08-30 | Plant Wide | in_progress
ELE-007 | 3.1.7 | electrical | Cable tray and ladder installation | 2026-07-20 | 2026-09-15 | Cable Routes | not_started
ELE-008 | 3.1.8 | electrical | Emergency diesel generator installation | 2026-09-01 | 2026-10-30 | DG Room | not_started
ELE-009 | 3.1.9 | electrical | Junction box and marshalling panel installation | 2026-08-15 | 2026-10-01 | Field Junction Areas | not_started
ELE-010 | 3.2.1 | electrical | Substation bus bar and switchgear installation | 2026-08-01 | 2026-10-15 | Main Substation | not_started
ELE-011 | 3.2.2 | electrical | Variable frequency drive VFD installation | 2026-09-15 | 2026-11-01 | VFD Room | not_started
ELE-012 | 3.2.3 | electrical | Fire alarm and detection system installation | 2026-09-01 | 2026-11-15 | Plant Wide | not_started